## Sheet1
| Milestones |  | Timeline | [5 empty] | Effort Matrix
|  |  | Task # | Task Description | Assignee | Estimated Time to Complete | Start Date | Completion Date | Task # | Assignee | Effort (%)
1 | Initial code commit | We will commit our initial code into GitHub allowing for us to start development by building off of eachother. | 1 | Research Project Management Software, research and set up whichever task tracker they see fit (JIRA, DevOps, etc..). | C. France | 1hr | 2023-01-05 | 2023-01-12 | 1 | C. France | 5
2 | Develop prototype | Develop a prototype for the app with basic functions. | 2 | Research stack to use and decide which stack to use. Something that all members are proficient in or familiar with. This will include 3-d body model library. | T. Swick | 0.5hr | 2023-01-05 | 2023-01-12 | 2 | T. Swick | 3
3 | User login | Create a user login page with a way to store login credentials. | 3 | Commit Initial Code Creation to the git repository. This way the team can fork it and start building. | T. Swick | 0.5hr | 2023-01-05 | 2023-01-12 | 3 | T. Swick | 3
4 | Creat human body model | Create the model that users will interact with and create routes to information on how to treat soreness in that area. | 4 | Design wireframes for application for planning out UI design for application and site. | C. Galang | 2hr | 2023-03-01 | 2023-03-22 | 4 | C. Galang | 10
5 | Storing user data | Determine a way to store data for returning users so that they can have continuity between sessions. | 5 | Develop application prototype for user interactions with application and site with Adobe XD. | C. Galang | 2hr | 2023-03-01 | 2023-03-15 | 5 | C. Galang | 10
6 | Testing | Perform various tests to insure all features work as intended. | 6 | Plan and implement the routing necessary for our application. | C. France | 2hr | 2023-01-12 | 2023-02-01 | 6 | C. France | 10
7 | User Testing/Feedback | Have selected users test the app and make changes that the users suggest. | 7 | Create a base landing page for us to work off of. | A. Huff | 1hr | 2023-02-14 | 2023-02-21 | 7 | A. Huff | 5
8 | Launch | Launch the app for public use. | 8 | Create the login page and implement logged-in or out state for routing. | A. Huff | 2hr | 2023-02-21 | 2023-03-01 | 8 | A. Huff | 10
|  |  | 9 | Implement the users table in the selected DB for IAM and hook it up to the login page. | T. Swick | 1hr | 2023-03-01 | 2023-03-08 | 9 | T. Swick | 5
|  |  | 10 | Create the database and setup necessary tables. | T. Swick | 1hr | 2023-02-01 | 2023-02-10 | 10 | T. Swick | 5
|  |  | 11 | Test database connection and queries are working and correct. | C. Galang | 1hr | 2023-02-14 | 2023-03-01 | 11 | C. Galang | 5
|  |  | 12 | Create the human body model to be used in application. | C. France | 3hr | 2023-02-14 | 2023-03-14 | 12 | C. France | 15
|  |  | 13 | List which body parts will be clickable on the body model and these parts will display information pertaining to assisting muscle soreness. | C. France | 2hr | 2023-01-15 | 2023-02-01 | 13 | C. France | 10
|  |  | 14 | Find videos and graphics describing various actions users can take to aide their soreness and ailments. | C. Galang | 2hr | 2023-03-17 | 2023-03-24 | 14 | C. Galang | 10
|  |  | 15 | Determine where discretion must be advised and how we will ensure no legal trouble over providing medical help. | A. Huff | 3hr | 2023-01-05 | 2023-01-26 | 15 | A. Huff | 15
|  |  | 16 | Develop and research questions that should and need to be asked to each user when using our app or site. | C. France | 1.5hr | 2023-01-05 | 2023-01-19 | 16 | C. France | 7
|  |  | 17 | Determine the best method for obtaining data from user and inputting into a database for our apps internal use. | T. Swick | 1hr | 2023-01-05 | 2023-01-12 | 17 | T. Swick | 5
|  |  | 18 | Perform functional tests to verify output of user’s interactions with the application. | C. Galang | 2hr | 2023-03-04 | 2023-03-11 | 18 | C. Galang | 10
|  |  | 19 | Conduct interviews with intended users interacting with the application to gauge areas of improvement. | A. Huff | 3hr | 2023-03-24 | 2023-04-15 | 19 | A. Huff | 15